## Daily Cost Tracker
Date | AWS Service | Operation Description | Units Used | Unit Cost ($) | Total Cost ($) | Notes/Learnings
2025-01-07 | S3 | Upload test documents | 10 | 0.005 | 0.05 | Uploaded 10 sample invoices
2025-01-07 | Textract | OCR processing - invoices | 15 | 0.15 | 2.25 | Tested on various invoice formats
2025-01-08 | Lambda | Document processing function | 50 | 2e-07 | 1e-05 | Testing trigger from S3
2025-01-08 | Comprehend | Entity extraction | 25 | 0.0001 | 0.0025 | Extracting vendor names, amounts
TOTAL DEVELOPMENT COST |  |  |  |  | 2.3025

## Cost Summary
AWS Document Processing Pipeline - Cost Summary
Development Phase Summary
Category | Estimated ($) | Actual ($) | Variance ($) |  | Phase 3 Costs:
S3 Storage | 0.5 | 0.05 | -0.45
Lambda Functions | 2 | 1e-05 | -2 |  | Date | Phase | Service | Resource | Usage | Cost | Notes
Textract | 7.5 | 2.25 | -5.25 |  | 2026-01-31 | Phase 3 | S3 | Uploads | 15 documents | 0 | Within Free Tier
Comprehend | 0.5 | 0.0025 | -0.4975 |  | 2026-01-31 | Phase 3 | Lambda | DocumentProcessor | 15 invocations | 0 | Within Free Tier
API Gateway | 0.1 | 0 | -0.1 |  | 2026-01-31 | Phase 3 | Textract | AnalyzeDocument | 12 pages | 0 | Within 1,000 page Free Tier
CloudWatch | 0.5 | 0 | -0.5 |  | 2026-01-31 | Phase 3 | Comprehend | Entity Detection | 12 documents | 0.013 | Within 50K unit Free Tier
Other Services | 0 | 0 | 0 |  | 2026-01-31 | Phase 3 | Comprehend | Sentiment Analysis | 12 documents | 0.013 | Within 50K unit Free Tier
Lambda (Tag Audit) | 0 | 0 | 0 |  | 2026-01-31 | Phase 3 | Comprehend | Key Phrases | 12 documents | 0.012 | Within 50K unit Free Tier
EventBridge | 0 | 0 | 0 | [5 empty] | Phase 3 Total | 0.038
TOTAL | 11.1 | 2.3025 | -8.7975
Cumulative Project Costs:
Monthly Production Cost Model (500 documents) |  |  |  |  | Phase | Time | Cost | Budget Remaining
[5 empty] | Pre-Dev Setup | 1 hour | 0 | 25
Service | Usage | Unit Cost | Monthly Cost ($) |  | Phase 1: S3 Infrastructure | 2 hours | 0 | 25
S3 Storage | 50 GB | $0.023/GB | 1.15 |  | Side Quest: Tag Governance | 1 hour | 0 | 25
S3 Requests | 3,000 requests | $0.005/1K PUT | 0.01 |  | Phase 3: Textract Testing | 3 hours | 0.038 | 24.96
Lambda | 1,500 invocations | $0.0000166667/GB-sec | 1.25 |  | Total | 7 hours | 0.038 | 24.96
Textract | 1,000 pages | $1.50/1K pages | 1.5
Comprehend | 100,000 units | $0.0001/unit | 10
API Gateway | 1,500 requests | $3.50/million | 0.01
CloudWatch Logs | 5 GB | $0.50/GB | 2
Lambda (Tag Audit) | 4 invocations/month | Free Tier | 0
EventBridge (Scheduled) | 1 rule | Free Tier | 0
Data Transfer | 10 GB out | $0.09/GB | 15.92
MONTHLY TOTAL |  |  | 13.92
ANNUAL COST |  |  | 24
ROI Analysis
| Manual Process | Automated Process
Monthly staff time (hours) | 25 | 4.2
Hourly rate | 25 | 25
Monthly labor cost | 0 | 2
Monthly AWS cost | 0 | 2
TOTAL MONTHLY COST | 0 | 0
Monthly Savings | 0 | 0
Annual Savings |  | 30000%
ROI % |  | 8.3333
Tag Governance Solution Comparison
Solution | Monthly Cost ($) | Annual Cost ($) | Status | Notes
AWS Config | 0.08 | 0 | ❌ Not Used | Too expensive for learning project
Lambda + EventBridge | 0 | 0 | ✅ Implemented | Within Free Tier - automated weekly audits
Manual Script | 0 | 0.96 | ⚠️ Backup | audit-tags.sh for on-demand checks
Annual Savings (Lambda vs Config) |  | 1

## Cost Alert Setup
AWS Cost Explorer & Budget Alert Setup Guide
Step 1: Enable Cost Explorer
1. Log into AWS Console
2. Navigate to: Billing Dashboard > Cost Explorer
3. Click 'Enable Cost Explorer'
4. Wait 24 hours for data population
Step 2: Create Budget Alert
1. Go to: Billing Dashboard > Budgets
2. Click 'Create budget'
3. Select 'Monthly cost budget'
4. Set budget amount: $25.00 (recommended)
5. Set alert threshold: 80% ($20.00)
6. Enter your email for notifications
Step 3: Daily Cost Tracking
1. Check Cost Explorer daily during development
2. Filter by service to see breakdown
3. Record costs in 'Daily Cost Tracker' sheet
4. Take screenshots for portfolio documentation
Recommended Alert Thresholds:
• 50% of budget: Warning email | Helps catch runaway costs early
• 80% of budget: Alert email | Time to review usage
• 100% of budget: Critical alert | Stop non-essential testing
Free Tier Limits to Monitor:
• Lambda: 1M requests/month | Track in Cost Explorer
• Textract: 1,000 pages/month (3 months) | Keep count in tracker
• Comprehend: 50K units/month (12 months) | Monitor usage closely
• S3: 5GB storage, 20K GET, 2K PUT | Check S3 metrics